## Sheet1
Sprint | Task | Start Date | End Date | Duration (Days) | Team Member
Sprint 1 | Setup Environment | Oct 1, 2024 | Oct 3, 2024 | 3 | Aryan Gandrath
Sprint 1 | UI/UX Design | Oct 2, 2024 | Oct 6, 2024 | 5 | Shreya Reddy Chidirala
Sprint 2 | Backend Development | Oct 5, 2024 | Oct 12, 2024 | 8 | Rohith Arikatla, Shreya Reddy Chidirala
Sprint 2 | Workout Plan Feature | Oct 9, 2024 | Oct 15, 2024 | 7 | Pravallika Gandla
Sprint 3 | Progress Tracker | Oct 13, 2024 | Oct 20, 2024 | 8 | Aryan Gandrath, Pravallika Gandla
Sprint 4 | Final Testing & QA | Oct 22, 2024 | Oct 29, 2024 | 8 | Rohith Arikatla
Sprint 4 | Deployment and Documentation | Oct 28, 2024 | Nov 1, 2024 | 5 | All members